## Instructions
This Excel workbook accompanies a post to LinkedIn… https://www.linkedin.com/pulse/use-earned-value-real-projects-greg-b-watson
SAP | Simulation of a report on timesheet hours as it would be produced by the company financial system
|  | - | Data Entry Tabs
Grades | Simulation of report of course milestone completions as it would be downloaded from a MOOD provider
EV | Automated calculation of earned value (EV) ratios based on the SAP, Grades, and Plan tabs
Q: How do we get from "EV" to "CallList"? A: The tab "CallList" lists the rows from the EV tab in order of their priority as determined by the calculations on the EV tab. Recall that the formula we apply for "estimate at completion" (EAC) assumes that each student will continue to study with the same efficiency until they complete. Thus the EAC = AC + (BAC - EV) / (CPI * SPI), the inclusion of SPI in the denominator that the schedule will extend in time until the course is complete Raw Priority = VAC = BAC - EAC A challenge with "raw priority" is that some rows may have the same VAC. For each row that has the same VAC, we add a small amount so that they are listed in sequence.
Plan | The syllabus as provided by the MOOC provider
CallList | A prioritized list of the people to call with a note of what to call about. Concept: With simple rules, you can create a list of people to call sequenced by the magnitude of their issues with a brief note what to call about. Such follow-up may nudge change to happen... or... if the nudge doesn't work, you should give warning that the change is not going to happen sooner than you could spot the problem without EV. | - | Action Items arising from EVM

## CallList
| AC | EV | PV | BAC | CV | SV | CPI | SPI | EAC | VAC | TCPI
Hrs | 209.9 | 138.75 | 270 | 1080 | -71.15 | -131.25 | 0.66103 | 0.51389 | 1633.8162 | -553.8162 | 1.0818 | <== Project Level (calculated from the 'EV' tab)
Rank | AC: Name; EV: What to talk about…
1 | AC: Fred; EV: May be having difficulty with the material
2 | AC: Kathy; EV: May be having difficulty with the material
3 | AC: Mona; EV: May be having difficulty with the material
4 | AC: Judy; EV: May be having difficulty with the material
5 | AC: Lynda; EV: May be having difficulty with the material
6 | AC: Ted; EV: May be having difficulty with the material
7 | AC: Henry; EV: May be having difficulty with the material
8 | AC: Tom; EV: May be having difficulty with the material
9 | AC: Mike; EV: May be having difficulty with the material
10 | AC: Dick; EV: May be having difficulty with the material
11 | AC: Stu; EV: May be having difficulty with the material
12 | AC: Harry; EV: Charging time to the wrong SAP code
13 | AC: Frank; EV: Not completing milestones in the week due
14 | AC: Bill; EV: Not completing milestones in the week due
15 | AC: Kurt; EV: Not completing milestones in the week due
16 | AC: Nancy; EV: Not completing milestones in the week due
17 | AC: Sue; EV: Doing well, may be able to coach others
18 | AC: Zoe; EV: Doing well, may be able to coach others
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## SAP
Person | Total | wk1 | wk2 | wk3 | wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21 | wk22 | wk23 | wk24 | wk25 | wk26 | wk27 | wk28 | wk29 | wk30 | wk31 | wk32 | wk33 | wk34 | wk35
Total | 209.9 | 54.8 | 56.8 | 61.8 | 36.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fred | 21 | 5 | 5 | 5 | 6
Sue | 14.9 | 3.8 | 3.8 | 3.8 | 3.5
Zoe | 13 | 3 | 4 | 3 | 3
Kurt | 9 | 4 | 0 | 4 | 1
Stu | 6 | 0 | 5 | 0 | 1
Frank | 14 | 5 | 5 | 4
Nancy | 4 | 0 | 0 | 3 | 1
Bill | 9 | 3 | 0 | 6 | 0
Ted | 7 | 3 | 2 | 1 | 1
Tom | 13 | 2 | 2 | 5 | 4
Dick | 12 | 1 | 5 | 5 | 1
Harry | 22 | 5 | 5 | 6 | 6
Mona | 8 | 3 | 2 | 1 | 2
Kathy | 10 | 6 | 2 | 1 | 1
Lynda | 14 | 2 | 6 | 2 | 4
Judy | 14 | 6 | 5 | 2 | 1
Henry | 13 | 1 | 5 | 6 | 1
Mike | 6 | 2 | 0 | 4 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Grades
| Design & Execute InfoSec Strategies | [9 empty] | InfoSec & Risk Management in Context | [9 empty] | Building an Info Risk Management Toolkit
Person | Quiz-1 | Quiz-2 | Quiz-3 | Quiz-4 | Assignment-1 | Quiz-5 | Quiz-6 | Quiz-7 | Quiz-8 | Assignment-2 | Quiz-1 | Quiz-2 | Quiz-3 | Quiz-4 | Assignment-1 | Quiz-5 | Quiz-6 | Quiz-7 | Quiz-8 | Assignment-2 | Quiz-1 | Quiz-2 | Quiz-3 | Quiz-4 | Assignment-1 | Quiz-5 | Quiz-6 | Quiz-7 | Quiz-8 | Assignment-2
Fred | 0.6 | 0.2 | 0.3 | 0.6
Sue | 0.9 | 0.6 | 0.7 | 0.8
Zoe | 0.8 | 0.8 | 0.8 | 0.8
Kurt | 1 | 0 | 1 | 0.26667
Stu | 0 | 1 | 0 | 0.26667
Frank | 1 | 1 | 1
Nancy | 0 | 0 | 0.8 | 0.26667
Bill | 0.8 | 0 | 1 | 0
Ted | 0.8 | 0.53333 | 0.26667 | 0.26667
Tom | 0.53333 | 0.53333 | 1 | 1
Dick | 0.26667 | 1 | 1 | 0.26667
Harry | 1 | 1 | 1 | 1
Mona | 0.8 | 0.53333 | 0.26667 | 0.53333
Kathy | 1 | 0.53333 | 0.26667 | 0.26667
Lynda | 0.53333 | 1 | 0.53333 | 1
Judy | 1 | 1 | 0.53333 | 0.26667
Henry | 0.26667 | 1 | 1 | 0.26667
Mike | 0.53333 | 0 | 1 | 0

## EV
| Design & Execute InfoSec Strategies | [9 empty] | InfoSec & Risk Management in Context | [9 empty] | Building an Info Risk Management Toolkit | [9 empty] | Earned Value | [10 empty] | Prioritization
Person | Quiz-1 | Quiz-2 | Quiz-3 | Quiz-4 | Assignment-1 | Quiz-5 | Quiz-6 | Quiz-7 | Quiz-8 | Assignment-2 | Quiz-1 | Quiz-2 | Quiz-3 | Quiz-4 | Assignment-1 | Quiz-5 | Quiz-6 | Quiz-7 | Quiz-8 | Assignment-2 | Quiz-1 | Quiz-2 | Quiz-3 | Quiz-4 | Assignment-1 | Quiz-5 | Quiz-6 | Quiz-7 | Quiz-8 | Assignment-2 | AC | EV | PV | BAC | CV | SV | CPI | SPI | EAC | TCPI | Suggested Topic for Counselling | RAW Priority = VAC | DeDuped Priority | Rank
Fred | 3.75 | 0 | 0 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 7.5 | 15 | 60 | -13.5 | -7.5 | 0.35714 | 0.5 | 168 | 1.3462 | May be having difficulty with the material | -108 | -108 | 1
Sue | 3.75 | 3.75 | 3.75 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.9 | 15 | 15 | 60 | 0.1 | 0 | 1.0067 | 1 | 59.6 | 0.99778 | Doing well, may be able to coach others | 0.4 | 0.4 | 17
Zoe | 3.75 | 3.75 | 3.75 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 15 | 15 | 60 | 2 | 0 | 1.1538 | 1 | 52 | 0.95745 | Doing well, may be able to coach others | 8 | 8 | 18
Kurt | 3.75 | 0 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 7.5 | 15 | 60 | -1.5 | -7.5 | 0.83333 | 0.5 | 72 | 1.0294 | Not completing milestones in the week due | -12 | -12 | 15
Stu | 0 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3.75 | 15 | 60 | -2.25 | -11.25 | 0.625 | 0.25 | 96 | 1.0417 | May be having difficulty with the material | -36 | -36 | 11
Frank | 3.75 | 3.75 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 11.25 | 15 | 60 | -2.75 | -3.75 | 0.80357 | 0.75 | 74.6667 | 1.0598 | Not completing milestones in the week due | -14.6667 | -14.6667 | 13
Nancy | 0 | 0 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3.75 | 15 | 60 | -0.25 | -11.25 | 0.9375 | 0.25 | 64 | 1.0045 | Not completing milestones in the week due | -4 | -4 | 16
Bill | 3.75 | 0 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 7.5 | 15 | 60 | -1.5 | -7.5 | 0.83333 | 0.5 | 72 | 1.0294 | Not completing milestones in the week due | -12 | -12.001 | 14
Ted | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 3.75 | 15 | 60 | -3.25 | -11.25 | 0.53571 | 0.25 | 112 | 1.0613 | May be having difficulty with the material | -52 | -52 | 6
Tom | 0 | 0 | 3.75 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 7.5 | 15 | 60 | -5.5 | -7.5 | 0.57692 | 0.5 | 104 | 1.117 | May be having difficulty with the material | -44 | -44 | 8
Dick | 0 | 3.75 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 7.5 | 15 | 60 | -4.5 | -7.5 | 0.625 | 0.5 | 96 | 1.0938 | May be having difficulty with the material | -36 | -36.001 | 10
Harry | 3.75 | 3.75 | 3.75 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 15 | 15 | 60 | -7 | 0 | 0.68182 | 1 | 88 | 1.1842 | Charging time to the wrong SAP code | -28 | -28 | 12
Mona | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 3.75 | 15 | 60 | -4.25 | -11.25 | 0.46875 | 0.25 | 128 | 1.0817 | May be having difficulty with the material | -68 | -68 | 3
Kathy | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3.75 | 15 | 60 | -6.25 | -11.25 | 0.375 | 0.25 | 160 | 1.125 | May be having difficulty with the material | -100 | -100 | 2
Lynda | 0 | 3.75 | 0 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7.5 | 15 | 60 | -6.5 | -7.5 | 0.53571 | 0.5 | 112 | 1.1413 | May be having difficulty with the material | -52 | -52.001 | 5
Judy | 3.75 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7.5 | 15 | 60 | -6.5 | -7.5 | 0.53571 | 0.5 | 112 | 1.1413 | May be having difficulty with the material | -52 | -52.002 | 4
Henry | 0 | 3.75 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 7.5 | 15 | 60 | -5.5 | -7.5 | 0.57692 | 0.5 | 104 | 1.117 | May be having difficulty with the material | -44 | -44.001 | 7
Mike | 0 | 0 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3.75 | 15 | 60 | -2.25 | -11.25 | 0.625 | 0.25 | 96 | 1.0417 | May be having difficulty with the material | -36 | -36.002 | 9
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Earned Value AC: 0; Earned Value EV: 0; Earned Value CPI: 0 |  | 0

## Plan
Wk | Element | Hrs | Cummu- lative
wk1 | Design & Execute InfoSec Strategies: Quiz-1 | 3.75 | 3.75
wk2 | Design & Execute InfoSec Strategies: Quiz-2 | 3.75 | 7.5
wk3 | Design & Execute InfoSec Strategies: Quiz-3 | 3.75 | 11.25
wk4 | Design & Execute InfoSec Strategies: Quiz-4 | 3.75 | 15
wk5 | Design & Execute InfoSec Strategies: Assignment-1 | 15 | 30
wk6 | Design & Execute InfoSec Strategies: Quiz-5 | 3.75 | 33.75
wk7 | Design & Execute InfoSec Strategies: Quiz-6 | 3.75 | 37.5
wk8 | Design & Execute InfoSec Strategies: Quiz-7 | 3.75 | 41.25
wk9 | Design & Execute InfoSec Strategies: Quiz-8 | 3.75 | 45
wk10 | Design & Execute InfoSec Strategies: Assignment-2 | 15 | 60
wk11 | InfoSec & Risk Management in Context: Quiz-1 | 3.75 | 63.75
wk12 | InfoSec & Risk Management in Context: Quiz-2 | 3.75 | 67.5
wk13 | InfoSec & Risk Management in Context: Quiz-3 | 3.75 | 71.25
wk14 | InfoSec & Risk Management in Context: Quiz-4 | 3.75 | 75
wk15 | InfoSec & Risk Management in Context: Assignment-1 | 15 | 90
wk16 | InfoSec & Risk Management in Context: Quiz-5 | 3.75 | 93.75
wk17 | InfoSec & Risk Management in Context: Quiz-6 | 3.75 | 97.5
wk18 | InfoSec & Risk Management in Context: Quiz-7 | 3.75 | 101.25
wk19 | InfoSec & Risk Management in Context: Quiz-8 | 3.75 | 105
wk20 | InfoSec & Risk Management in Context: Assignment-2 | 15 | 120
wk21 | Building an Info Risk Management Toolkit: Quiz-1 | 3.75 | 123.75
wk22 | Building an Info Risk Management Toolkit: Quiz-2 | 3.75 | 127.5
wk23 | Building an Info Risk Management Toolkit: Quiz-3 | 3.75 | 131.25
wk24 | Building an Info Risk Management Toolkit: Quiz-4 | 3.75 | 135
wk25 | Building an Info Risk Management Toolkit: Assignment-1 | 15 | 150
wk26 | Building an Info Risk Management Toolkit: Quiz-5 | 3.75 | 153.75
wk27 | Building an Info Risk Management Toolkit: Quiz-6 | 3.75 | 157.5
wk28 | Building an Info Risk Management Toolkit: Quiz-7 | 3.75 | 161.25
wk29 | Building an Info Risk Management Toolkit: Quiz-8 | 3.75 | 165
wk30 | Building an Info Risk Management Toolkit: Assignment-2 | 15 | 180

## Reference (hidden)
Counselling
Code | Description
Doing well, may be able to coach others
cost | Charging time to the wrong SAP code
sched | Not completing milestones in the week due
know | May be having difficulty with the material